## Agenda
Sprint Planning Meeting 1 |  |  |  | Notes:
Group Number: | 1 |  |  | Replace ## actual sprint planning number and group number respectively.
This spreadsheet contains more than one sheet; after you are done with Attendees information, complete information on sheet "Current Sprint"
Attendees (Last name, First Name) | Present | Absent | Notes/Comments | Complexity and number of items must be reasonable according to the number of team members.
Mokhurenko, Yaroslav | X |  | Everyone should draw their draft of the design for the app and choose the best one on the next meeting. | Your professor might ask you to add more user stories and or increase complexity/functionality.
Derbishev, Temirlan | X |  |  | "Current Sprint" information will be used as a checklist to grade your sprint release.
Diaz-Vargas, Nicolas | X
Patel, Jay | X
Bikov, Aleksei | X
Add a screenshot of your "Agile Task Board" below:

## Current Sprint
Sprint 1 |  |  |  |  | Group Number: | 1 |  |  | Notes:
Feel free to replace below table with your CSV export, make sure to format table as needed in order to support column filtering | [8 empty] | Bring information from your product backlog to identify "user stores" that will become part of your current sprint release. You can copy paste or replace table entirely using your CSV export. You can as change column names to match your format as needed.
Row # | ID | As a/an | I want to… | so that… | Notes | Priority | Status | Owner
1 | FYF-1 | Student | Register in the app | Continue to creating my profile |  |  | In Progress
2 | FYF-13 | Student | Edit my profile | Maintain the accuracy of my personal |  |  | In Progress
3 | FYF-2 | Student | Fill in details about myself (Name, Gender, Age, College/University, Country of origin etc). | Complete creating my profile |  |  | In Progress
4 | FYF-10 | Student | Create a post on my page | Share content with my friendlist |  |  | In Progress
5 | FYF-33 | Student | Fast sign up with google account | Faster/easier sign up |  |  | In Progress
6 | FYF-15 | Student | Login into account | Have access to my account |  |  | In Progress
7 | FYF-34 | Student | Share my current status | So people know what I am up to |  |  | In Progress
8 | FYF-39 | Student | Create a burger menu for mobile view | For people coming to site from mobiles |  |  | In Progress
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Technology
Questions: | Answers
Front End Technology? | i.e. Angular, React, Laravel, Pure PHP, etc. React
Are you using or plan to use a Data Base? | Yes
If Yes which DB engine are you using? | i.e. MariaDB, Mysql, Mongo DB, etc. Firebase
Which application server are you using? | i.e. Apache, Nodejs, Nginx, etc. Nginx
Describe here any additional technologies | Maybe some AWS free tier services
Additional Notes | ReactJS additional packages, e.g. axios for http requsts to endpoints.